## Data Transformation
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
Gemini | Task 1 | Wood | 2020-02-17 | 5 | 2020-02-21 | 2 | 40% | 218000 | 97337
Gemini | Task 2 | Samora | 2020-02-17 | 6 | 2020-02-24 | 3 | 50% | 393000 | 177440
Gemini | Task 3 | Mc Fay | 2020-02-18 | 10 | 2020-03-02 | 4 | 40% | 86000 | 31046
Gemini | Task 4 | Ladd | 2020-02-21 | 9 | 2020-03-04 | 3 | 33.33% | 732000 | 261324
Gemini | Task 5 | Hirsch | 2020-02-17 | 4 | 2020-02-20 | 1 | 25% | 492000 | 116850
Gemini | Task 6 | Wood | 2020-02-20 | 6 | 2020-02-27 | 0 | 0% | 188000 | 0
Gemini | Task 7 | Samora | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 180000 | 79380
Gemini | Task 8 | Mc Fay | 2020-02-24 | 5 | 2020-02-28 | 2 | 40% | 582000 | 195231
Gemini | Task 9 | Ladd | 2020-02-24 | 9 | 2020-03-05 | 1 | 11.11% | 562000 | 74746
Gemini | Task 10 | Hirsch | 2020-02-24 | 6 | 2020-03-02 | 3 | 50% | 416000 | 175015
Orion | Task 1 | Wood | 2020-02-18 | 7 | 2020-02-26 | 7 | 100% | 293000 | 273001
Orion | Task 2 | Samora | 2020-02-17 | 9 | 2020-02-27 | 4 | 44.44% | 224000 | 57910
Orion | Task 3 | Mc Fay | 2020-02-18 | 8 | 2020-02-27 | 0 | 0% | 978000 | 0
Orion | Task 4 | Ladd | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 932000 | 379157
Orion | Task 5 | Hirsch | 2020-02-21 | 4 | 2020-02-26 | 1 | 25% | 854000 | 322812
Orion | Task 6 | Wood | 2020-02-21 | 6 | 2020-02-28 | 3 | 50% | 81000 | 38461
Orion | Task 7 | Samora | 2020-02-24 | 6 | 2020-03-02 | 5 | 83.33% | 169000 | 136468
Orion | Task 8 | Mc Fay | 2020-02-25 | 4 | 2020-02-28 | 1 | 25% | 61000 | 12078
Orion | Task 9 | Ladd | 2020-02-27 | 7 | 2020-03-06 | 3 | 42.86% | 645000 | 273048
Orion | Task 10 | Hirsch | 2020-02-17 | 3 | 2020-02-19 | 3 | 100% | 68000 | 64987
Vega | Task 1 | Wood | 2020-02-17 | 10 | 2020-02-28 | 5 | 50% | 839000 | 406974
Vega | Task 2 | Samora | 2020-02-21 | 5 | 2020-02-27 | 4 | 80% | 729000 | 487139
Vega | Task 3 | Mc Fay | 2020-02-24 | 7 | 2020-03-03 | 3 | 42.86% | 826000 | 298186
Vega | Task 4 | Ladd | 2020-02-26 | 7 | 2020-03-05 | 2 | 28.57% | 895000 | 280583
Vega | Task 5 | Hirsch | 2020-02-28 | 3 | 2020-03-03 | 2 | 66.67% | 341000 | 129785
Open AI | Task 1 | Wood | 2020-03-02 | 9 | 2020-03-12 | 8 | 88.89% | 787000 | 727188
Open AI | Task 2 | Samora | 2020-03-02 | 10 | 2020-03-13 | 2 | 20% | 228000 | 47880
Open AI | Task 3 | Mc Fay | 2020-02-17 | 4 | 2020-02-20 | 0 | 0% | 147000 | 0
Open AI | Task 4 | Ladd | 2020-02-19 | 8 | 2020-02-28 | 5 | 62.5% | 338000 | 205123
Open AI | Task 5 | Hirsch | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 857000 | 305949
Open AI | Task 6 | Wood | 2020-02-25 | 6 | 2020-03-03 | 3 | 50% | 602000 | 322371
Open AI | Task 7 | Samora | 2020-02-25 | 4 | 2020-02-28 | 2 | 50% | 990000 | 451440
Alpha | Task 1 | Mc Fay | 2020-02-28 | 8 | 2020-03-10 | 3 | 37.5% | 96000 | 32256
Alpha | Task 2 | Ladd | 2020-03-02 | 9 | 2020-03-12 | 4 | 44.44% | 513000 | 226233
Alpha | Task 3 | Hirsch | 2020-02-20 | 5 | 2020-02-26 | 3 | 60% | 616000 | 401579
Alpha | Task 4 | Wood | 2020-02-19 | 3 | 2020-02-21 | 3 | 100% | 817000 | 807069
Alpha | Task 5 | Samora | 2020-02-21 | 7 | 2020-03-02 | 3 | 42.86% | 372000 | 173166
Alpha | Task 6 | Mc Fay | 2020-02-24 | 10 | 2020-03-06 | 2 | 20% | 50000 | 8400
Alpha | Task 7 | Ladd | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 807000 | 262679
Alpha | Task 8 | Hirsch | 2020-02-24 | 3 | 2020-02-26 | 0 | 0% | 691000 | 0
Formulas:
End Date = WORKDAY.INTL(Table1[[#This Row],[Start Date]]-1,Table1[[#This Row],[Duration]],1)

## Project
Project Management Dashboard |  |  |  | 17-February-20 to 13-March-20
Project | Manager | Task | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
Alpha | Hirsch | Task 3 | 2020-02-20 | 5 | 2020-02-26 | 3 | 60% | 616000 | 401579
|  | Task 8 | 2020-02-24 | 3 | 2020-02-26 | 0 | 0% | 691000 | 0
| Ladd | Task 2 | 2020-03-02 | 9 | 2020-03-12 | 4 | 44.44% | 513000 | 226233
|  | Task 7 | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 807000 | 262679
| Mc Fay | Task 1 | 2020-02-28 | 8 | 2020-03-10 | 3 | 37.5% | 96000 | 32256
|  | Task 6 | 2020-02-24 | 10 | 2020-03-06 | 2 | 20% | 50000 | 8400
| Samora | Task 5 | 2020-02-21 | 7 | 2020-03-02 | 3 | 42.86% | 372000 | 173166
| Wood | Task 4 | 2020-02-19 | 3 | 2020-02-21 | 3 | 100% | 817000 | 807069
Gemini | Hirsch | Task 10 | 2020-02-24 | 6 | 2020-03-02 | 3 | 50% | 416000 | 175015
|  | Task 5 | 2020-02-17 | 4 | 2020-02-20 | 1 | 25% | 492000 | 116850
| Ladd | Task 4 | 2020-02-21 | 9 | 2020-03-04 | 3 | 33.33% | 732000 | 261324
|  | Task 9 | 2020-02-24 | 9 | 2020-03-05 | 1 | 11.11% | 562000 | 74746
| Mc Fay | Task 3 | 2020-02-18 | 10 | 2020-03-02 | 4 | 40% | 86000 | 31046
|  | Task 8 | 2020-02-24 | 5 | 2020-02-28 | 2 | 40% | 582000 | 195231
| Samora | Task 2 | 2020-02-17 | 6 | 2020-02-24 | 3 | 50% | 393000 | 177440
|  | Task 7 | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 180000 | 79380
| Wood | Task 1 | 2020-02-17 | 5 | 2020-02-21 | 2 | 40% | 218000 | 97337
|  | Task 6 | 2020-02-20 | 6 | 2020-02-27 | 0 | 0% | 188000 | 0
Open AI | Hirsch | Task 5 | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 857000 | 305949
| Ladd | Task 4 | 2020-02-19 | 8 | 2020-02-28 | 5 | 62.5% | 338000 | 205123
| Mc Fay | Task 3 | 2020-02-17 | 4 | 2020-02-20 | 0 | 0% | 147000 | 0
| Samora | Task 2 | 2020-03-02 | 10 | 2020-03-13 | 2 | 20% | 228000 | 47880
|  | Task 7 | 2020-02-25 | 4 | 2020-02-28 | 2 | 50% | 990000 | 451440
| Wood | Task 1 | 2020-03-02 | 9 | 2020-03-12 | 8 | 88.89% | 787000 | 727188
|  | Task 6 | 2020-02-25 | 6 | 2020-03-03 | 3 | 50% | 602000 | 322371
Orion | Hirsch | Task 10 | 2020-02-17 | 3 | 2020-02-19 | 3 | 100% | 68000 | 64987
|  | Task 5 | 2020-02-21 | 4 | 2020-02-26 | 1 | 25% | 854000 | 322812
| Ladd | Task 4 | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 932000 | 379157
|  | Task 9 | 2020-02-27 | 7 | 2020-03-06 | 3 | 42.86% | 645000 | 273048
| Mc Fay | Task 3 | 2020-02-18 | 8 | 2020-02-27 | 0 | 0% | 978000 | 0
|  | Task 8 | 2020-02-25 | 4 | 2020-02-28 | 1 | 25% | 61000 | 12078
| Samora | Task 2 | 2020-02-17 | 9 | 2020-02-27 | 4 | 44.44% | 224000 | 57910
|  | Task 7 | 2020-02-24 | 6 | 2020-03-02 | 5 | 83.33% | 169000 | 136468
| Wood | Task 1 | 2020-02-18 | 7 | 2020-02-26 | 7 | 100% | 293000 | 273001
|  | Task 6 | 2020-02-21 | 6 | 2020-02-28 | 3 | 50% | 81000 | 38461
Vega | Hirsch | Task 5 | 2020-02-28 | 3 | 2020-03-03 | 2 | 66.67% | 341000 | 129785
| Ladd | Task 4 | 2020-02-26 | 7 | 2020-03-05 | 2 | 28.57% | 895000 | 280583
| Mc Fay | Task 3 | 2020-02-24 | 7 | 2020-03-03 | 3 | 42.86% | 826000 | 298186
| Samora | Task 2 | 2020-02-21 | 5 | 2020-02-27 | 4 | 80% | 729000 | 487139
| Wood | Task 1 | 2020-02-17 | 10 | 2020-02-28 | 5 | 50% | 839000 | 406974
Grand Total | [7 empty] | 19695000 | 8340291
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Functions
Info. |  | Values |  | Info. |  | Values |  | %
Not Started | 4 | Sum of Days completed | 112 | Days completed | 42.11% | Sum of Actual | 8340291 | 42.35%
In Progress | 33 | Sum of Duration | 266 | Days Remaining | 57.89% | Sum of Budget | 19695000 | 57.65%
Completed | 3
Remaining | 37
Total Tasks | 40

## Insights
Insights :
The current progress rates across progress are follows:
Vega leads at 55.33%, followed by Orion at 51.3% , Open AI at 43.14%, Alpha 41.87% , and Gemini at 33.2%,
Vega and Orion as the most advanced, while Gemini requires additional focus to improve its progress.
Out of allocated 19.7M budget, 8.3M has been utilized so far.
Over all progress rate in the department is approximately 42.11%.
Out of allocated 19.7M budget, 8.3M has been utilized so far.
Currently, 33 projects are in progress. 3 projects are done and 4 have yet to start ,
We have utilized 42.11% of the overall timeline reflecting steady advancement toward our goals.